## How to Use
How to Use the Asset Inventory Starter Kit (Step-by-Step)
This template is designed to scale from startups to CTEM-ready enterprises. STEP 1 - Start with Production & Internet-Facing Assets • Add one row per asset in the Asset Inventory sheet • Populate all GREEN columns first • Focus on Production, Vendor, and Internet-Facing systems STEP 2 - Assign Ownership and Context • Every asset must have an owner team • Classify business criticality and data sensitivity STEP 3 - Use the 30–60–90 Playbook • Read the Playbook tab to understand sequencing and decisions • Use the Execution Tracker tab to assign owners, dates, and status STEP 4 - Verify and Maintain • Keep Last Verified Date current • Use Verification Status to identify stale assets STEP 5 - Scale to CTEM • Add lifecycle, exposure, change, and risk linkage fields • Use inventory outputs to drive audits, pentests, and remediation

## Asset Inventory
Asset ID | Asset Name | Asset Category | Asset Type | Environment | In Scope for Security Assessments | Primary Owner | Owner Department | Business Unit | Vendor Owner | Business Criticality | Data Sensitivity | Regulatory Impact | Customer-Facing | Internet-Facing | Access Boundary | Third-Party Accessible | Exposure Type | Asset Lifecycle Status | Deployment Date | Decommission Date | Discovery Source | Verification Status | Last Verified Date | Verified By | Confidence Level | Last Change Detected Date | Change Source | Change Reviewed | Linked Risk / Finding ID | Risk Severity | Remediation SLA | Audit Evidence Reference
APP-001 | Customer Web Application | Cloud | Web Application | Production | Yes | Application Team | Engineering | Product |  | Mission Critical | Customer Data |  | Yes | Yes | Authenticated |  | Web | Active |  |  | Cloud API | Verified <=90 days |  |  | High
DB-001 | Primary Customer Database | Cloud | Database | Production | Yes | Data Platform Team | Engineering | Product |  | High | PII |  | No | No | Internal |  | Database | Active |  |  | Cloud API | Verified <=90 days |  |  | High
SaaS-001 | Customer Support Platform | SaaS | SaaS Application | Vendor | Yes | IT Operations | IT | Operations |  | Medium | Customer Data |  | Indirect | Yes | Authenticated |  | SaaS | Active |  |  | Procurement | Verified <=180 days |  |  | Medium

## 30–60–90 Playbook
2026 Asset Inventory: 30-60-90 Day Playbook
This playbook is the step-by-step guide for building a complete, defensible asset inventory. It explains WHAT to do and WHY. Use the '30-60-90 Execution Tracker' to manage owners, dates, and status.
Phase | Objective | Step-by-Step Actions | Key Decisions | Outputs / Artifacts | Common Pitfalls
Days 0-30 | Establish scope, baseline visibility, and ownership | 1. Define in-scope environments (Prod/Dev/Test/Vendor) 2. Agree on asset categories and minimum required fields 3. Identify authoritative sources (cloud APIs, CMDB, SSO, procurement) 4. Discover cloud, on‑prem, and SaaS assets 5. Populate inventory for Production and Internet‑Facing assets first 6. Assign owners for critical systems 7. Set verification cadence and capture Last Verified Date | • What is explicitly in vs out of scope? • Which source is authoritative when data conflicts? • Who is accountable for each critical asset? | • Baseline inventory (Prod + Internet‑Facing) • Ownership coverage for top systems • Initial stale/orphaned list | • Trying to inventory everything at once • Allowing assets without owners • Treating inventory as a one‑time task
Days 31-60 | Normalize data and enrich with business and exposure context | 1. Deduplicate assets across sources 2. Normalize naming and Asset IDs 3. Classify business criticality and data sensitivity 4. Identify Internet‑Facing assets and access boundaries 5. Add vendor‑managed systems and assign vendor owners 6. Generate audit and pentest scope directly from inventory | • What makes an asset business‑critical? • Which assets truly expand the attack surface? • Which vendors are in scope for assessments? | • Enriched inventory with context and exposure • Validated pentest / audit scope • Vendor inventory with ownership | • Over‑classifying everything as high risk • Missing vendor‑operated systems • Still relying on side spreadsheets
Days 61-90 | Operationalize lifecycle, change awareness, and risk linkage (CTEM‑ready) | 1. Enforce lifecycle status (Active / Deprecated / Decommissioned) 2. Capture change signals for key systems (manual → automated) 3. Link findings and remediation SLAs to assets 4. Attach audit evidence to in‑scope systems 5. Establish recurring reporting and governance cadence | • When is an asset truly decommissioned? • Which changes require inventory updates? • How does inventory feed risk prioritization? | • Change‑aware inventory • Risk‑linked assets with SLAs • Audit‑ready evidence trail • Letting lifecycle fields rot • Treating inventory separate from risk • No ownership for ongoing updates

## 30–60–90 Execution Tracker
2026 Asset Inventory Kickoff: 30-60-90 Day Plan (CTEM-Ready)
Use this tab as your execution plan. It is prefilled with recommended tasks, sequencing, and KPIs. Tip: Start with Production + Internet-Facing assets, then expand coverage and governance.
Phase | Week | Workstream | Task | Owner | Dependencies | Sources / Tools | Deliverable | Success Metric (KPI) | Priority | Status | Start Date | Due Date | Notes
0–30 | W1 | Program Setup | Define in-scope environments & boundaries (Prod/Dev/Test/Vendor); confirm exclusions |  |  | Security leadership; compliance; IT | Scope statement + boundary notes | Scope agreed by Security + Compliance | High | Not Started
0–30 | W1 | Program Setup | Define asset categories & minimum required fields (GREEN); publish naming convention for Asset ID |  |  | Template; internal standards | Inventory data standard (1 pager) | Standard approved; shared with owners | High | Not Started
0–30 | W1 | Source Mapping | List authoritative sources: cloud APIs, CMDB/ITSM, endpoint tool, SSO/procurement, vendor list |  |  | AWS/Azure/GCP; CMDB; Okta; finance/procurement | Source map (what feeds inventory) | ≥5 key sources identified | High | Not Started
0–30 | W2 | Discovery | Run cloud discovery (accounts/subscriptions/projects) and export compute/storage/db/functions |  | Source map complete | Cloud APIs; CSP inventory exports | Initial cloud asset export | Covers ≥80% cloud projects/accounts | High | Not Started
0–30 | W2 | Discovery | Run network discovery for on-prem (or ingest existing); identify unknown hosts |  | Network access | Network scanner; IPAM; DNS | On-prem/Network asset export | Unknown hosts list created | Medium | Not Started
0–30 | W2 | SaaS Discovery | Pull SaaS list from SSO + procurement + expense; flag shadow SaaS |  | Source map complete | SSO reports; finance; CASB (if any) | Initial SaaS catalog | Top SaaS apps identified; shadow list started | High | Not Started
0–30 | W3 | Data Load | Populate Asset Inventory: all known Production + Internet-Facing assets (GREEN columns only) |  | Discovery exports available | This spreadsheet; imports; copy/paste | Baseline inventory populated | ≥80% production assets entered | High | Not Started
0–30 | W3 | Ownership | Assign owners for Top 20 critical assets; identify orphaned assets |  | Baseline inventory | Eng leads; app owners | Owner coverage report | Owners for Top 20; orphans <10% | High | Not Started
0–30 | W4 | Verification | Set verification cadence/SLA (e.g., 90 days); start populating Last Verified Date |  | Baseline inventory | Security ops; governance | Verification policy + initial verification | ≥50% of baseline verified | Medium | Not Started
0–30 | W4 | Quick Wins | Identify obvious decommission candidates + duplicate systems; create cleanup backlog |  | Baseline inventory | CMDB; cloud cost; owners | Decommission backlog + shortlist | ≥10 cleanup items identified | Medium | Not Started
31–60 | W5 | Normalization | Deduplicate assets across sources; normalize naming and IDs; resolve conflicts |  | Baseline inventory + exports | Spreadsheet; CMDB; cloud | Deduped inventory v1 | Duplicates reduced to <2% | High | Not Started
31–60 | W5 | Context | Fill business criticality + data sensitivity for all Production assets |  | Owner assignments | Owners; data owners | Context-enriched inventory | ≥95% production has criticality/sensitivity | High | Not Started
31–60 | W6 | Exposure | Classify Internet-Facing, Access Boundary, Exposure Type; verify with edge/WAF/DNS |  | Baseline inventory | DNS; WAF; cloud edge; EASM | Exposure classification completed | 100% internet-facing identified and reviewed | High | Not Started
31–60 | W6 | Vendors | Add vendor-managed systems; assign vendor owner; capture evidence (SOC2/pen test) |  | Vendor list | Vendor catalog; GRC; procurement | Vendor inventory + evidence links | Top vendors accounted for; owners assigned | Medium | Not Started
31–60 | W7 | Audit/Pentest Scope | Generate pentest scope list directly from inventory; validate with stakeholders |  | Exposure + context complete | Inventory filters/exports | Pentest scope export + sign-off | Scope validated without manual hunting | High | Not Started
31–60 | W7 | Governance | Define registration rule for new assets (CI/CD, cloud account onboarding, SaaS request) |  |  | Change mgmt; SDLC; ITSM | Asset onboarding SOP | New assets captured within 7 days | Medium | Not Started
31–60 | W8 | Verification | Introduce Verification Status + Confidence; report stale/unverified assets |  | Verification policy | This sheet; reporting | Stale asset report | Stale items visible; action owners assigned | Medium | Not Started
61–90 | W9 | Change Awareness | Add Change Source + Last Change Detected for top systems (manual to start) |  | Onboarding SOP | CI/CD; cloud logs; manual | Change-aware inventory (Top systems) | ≥80% of critical systems have change fields | High | Not Started
61–90 | W10 | Lifecycle | Enforce Asset Lifecycle Status; set Decommission dates for approved items |  | Cleanup backlog | Owners; IT; cloud | Lifecycle governance in place | Deprecated/decommissioned removed from scope | High | Not Started
61–90 | W11 | Risk Linkage | Link top findings to assets (Linked Risk/Finding ID) and assign Remediation SLA |  | Vuln mgmt/GRC list | Jira/GRC/Vuln tool | Risk-linked inventory (Top findings) | Top 20 findings linked to assets | High | Not Started
61–90 | W12 | Evidence | Add Audit Evidence Reference for in-scope systems (policies, diagrams, reports) |  | Audit needs list | GRC; drive links | Evidence-backed inventory | Auditor can trace asset→evidence | Medium | Not Started
61–90 | W13 | Reporting | Create monthly exec metrics: coverage, exposure, stale assets, orphans, lifecycle cleanup |  | Inventory stable | This sheet; pivots | Monthly inventory scorecard | Metrics reviewed monthly | Medium | Not Started
61–90 | W13 | Handoff | Decide whether to operationalize in a system of record (CTEM) or keep spreadsheet |  | Reporting + governance | Security leadership | Decision memo + roadmap | Owner-approved operating model | Low | Not Started

## Checklist
Self-Assessment Checklist (Inventory Maturity)
Check all that apply:
# | Checklist Item | Status (Yes/No) | Notes
1 | Complete inventory covering cloud, SaaS, on-prem, APIs, vendors, and endpoints
2 | Every asset has a defined owner team and business unit
3 | Pentest and audit scope can be generated directly from the inventory
4 | Assets are consistently tagged for criticality, data sensitivity, and exposure
5 | Assets are linked to risk records, remediation SLAs, and audit evidence
6 | Stale or unverified assets can be identified automatically (verification status + last verified)
7 | Inventory updates are driven by change events, not just annual reviews
8 | Each asset has an explicit lifecycle status (active/deprecated/decommissioned)
9 | External exposure is first-class (internet-facing, access boundary, third-party accessible)
10 | Discovery source and confidence/verification are documented for each asset

## Maturity Levels
Inventory Maturity Levels
Level | Name | What it looks like | Key requirements
Level 1 | Reactive Inventory | Partial list; manual; scope gaps common | Basic identity + owners for key production assets
Level 2 | Structured Inventory | Broad coverage; consistent fields; periodic updates | Categories, environment, criticality/sensitivity, last verified
Level 3 | Security-Driven Inventory | Inventory drives audits/pentests; exposure tracked | Internet-facing + access boundary; risk links begin
Level 4 | Continuous / CTEM-Ready Inventory | Change-aware; evidence-backed; lifecycle governed | Change detection fields; verification status; lifecycle + evidence/SLA linkage

## Control Mapping
Control Mapping (SOC 2 / ISO 27001 / PCI DSS)
Use this tab to demonstrate how the inventory supports audit expectations. Control IDs are common references; confirm with your auditor.
Inventory Capability | SOC 2 (TSC) | ISO 27001:2022 | PCI DSS v4.0 | Notes / Evidence
Maintain complete asset inventory + boundaries | CC1.2, CC2.1 | A.5.9 | 2.2.4, 12.5.1 | Inventory export + scope statement
Assign ownership for each asset | CC1.1, CC2.2 | A.5.9 | 12.5.1 | Owner field populated
Asset classification (criticality/sensitivity) | CC3.1 | A.5.12 | 12.3.1 | Tags + classification report
Change awareness / updates | CC8.1 | A.8.32 | 6.4.2 | Change source + last change detected
Vendor systems & responsibilities | CC9.2 | A.5.19, A.5.20 | 12.8 | Vendor owner + evidence links
Risk linkage + remediation SLA | CC3.2, CC5.3 | Clause 6.1.2 | 6.3.3, 12.10.5 | Risk ID + SLA + evidence reference

## DO NOT EDIT – Dropdowns
Asset Category | Environment | Yes/No | Customer-Facing | Access Boundary | Exposure Type | Asset Lifecycle Status | Business Criticality | Data Sensitivity | Discovery Source | Verification Status | Confidence Level | Change Source | Risk Severity | Remediation SLA | Regulatory Impact | Asset Type (Suggested)
On-Prem | Production | Yes | Yes | Unauthenticated | Web | Planned | Low | None | Cloud API | Verified ≤90 days | High | CI/CD | Low | 7 Days | None | Web Application
Cloud | Development | No | No | Authenticated | API | Active | Medium | Internal | CMDB | Verified ≤180 days | Medium | Cloud Drift | Medium | 30 Days | SOC 2 | API
SaaS | Test |  | Indirect | Internal | Database | Deprecated | High | PII | Network Scan | Unverified | Low | Manual Update | High | 90 Days | ISO 27001 | Database
API | Vendor |  |  |  | Admin Console | Decommissioned | Mission Critical | PCI | Procurement | Exception Approved |  | Vendor Notification | Critical | Accepted Risk | PCI DSS | SaaS Application
Vendor |  |  |  |  | SaaS | Orphaned |  | PHI | Vendor Attestation | [5 empty] | HIPAA | VM
Endpoint |  |  |  |  | VPN |  |  | Customer Data | Manual | [5 empty] | HITRUST | Container
Server
Function